ONE-PAGE PLAN · LEDGER SERVICE (04)

Ledger Service — Overview & Milestone Breakdown

Java 21 / Spring Boot 3.3 · PostgreSQL 16 append-only · Ledger & Money Movement squad · critical path · ≈4–5 sprints between gates M1 and M2 · incorporates ADR-0002

Overview

The Ledger is the system of record for value — nothing else in the platform may hold a balance. Money is recorded as balanced, double-entry, append-only journals; balances are projections derived from postings, never stored and mutated. It runs on the JVM for exact integer-minor-unit arithmetic and posting throughput, and serves both applications. It does not price (10), orchestrate (05) or manage exchange rates: a locked rate arrives as an input to every posting.

Features broken down by milestone

| Milestone | Features delivered | Exit criterion (must be demonstrated) |
| --- | --- | --- |
| L0 — Ready to start (entry gate) | None — gate only | Gate M1 passed; JVM template scaffolds a passing service; Persistence-Java available |
| L1 — Money & domain core 1 sprint | Money value object · journal/posting model · balancing invariant · reversal semantics · rate scale-8 + no-rate-lookup rules | Unbalanced journal rejected in-domain; jqwik tests pass; no float type exists; ArchUnit green incl. no posting-path FxRatePort call |
| L2 — Posting & append-only 1 sprint | JP1 post · JP2 idempotency · JP3 append-only · JP4 reversal · FX1 quote_id · FX2 display_meta · outbox | DB denies UPDATE/DELETE; same key never double-posts; kill mid-write leaves both rows or neither; display_meta matches its quote |
| L3 — Holds 1 sprint | HD1 place · HD2 capture · HD3 release · HD4 expiry | All transitions idempotent and audited; a released hold can never be captured; expiry runs on schedule |
| L4 — Balances & projection 1 sprint | BL1 projection · BL2 cached read · BL3 nightly reconciliation · BL4 as-of balance | Balances rebuildable from empty; cached read within outbox-lag budget; job detects injected drift |
| L5 — Consumer ready 1 sprint | Reversal endpoint · perf tuning · Pact contracts · isolation & residency checks · FX3/FX4 conversion behind a flag | Post p99 < 200 ms, read p99 < 50 ms; Pact green for Payments/Wallets/Pricing; isolation green; KSA in-Kingdom proven; runbook written |

Applies to every milestone

- Integer minor units only — no floating-point arithmetic anywhere.

- Journals immutable: corrections are reversals, never edits or deletes.

- Every mutation idempotency-keyed; every state change emitted via the outbox in the same transaction.

- Rates arrive as inputs — the posting path never calls FxRatePort (ADR-0002 D6). ArchUnit + isolation suite blocking in CI.

Scope & focus. FX_CONVERSION and FX-Position accounts are built in L5 but stay behind a capability flag — the PK pilot books PKR only (ADR-0002 D7). Protect L2: append-only storage, idempotency and the outbox are cheap now, expensive to retrofit.